## Product Backlog
ID | Added in sprint | Closed in sprint | As a/an | I want to… | Responsible | Process
1 | 1 | 2 | manager | view all the claim | Sang | Done
2 | 3 | 3 | manager | view report | Sang | Done
3 | 2 | 2 | Coordinator | manage process for the faculty | Sang | Done
4 | 3 | 3 | Coordinator | disable all claims uploading after closure date | Tuan | Done
5 | 3 | 3 | Coordinator | allow student upload evidence after closure date until final closure date | Tuan | Done
6 | 2 | 2 | Coordinator | receive a notification when there is a new claim | Tuan | Done
7 | 2 | 4 | Coordinator | process the claim before 14 days since the upload date. | Tuan | Done
8 | 3 | 3 | Coordinator | access student claim in my faculty | Sang | Done
9 | 2 | 2 | Coordinator | belong the faculty | Sang | Done
10 | 2 | 2 | student | upload one or more the EC claim | Tuấn | Done
11 | 3 | 3 | student | all of EC uploaded claim have to contain PDF or Image evidence. | Tuan | Done
12 | 3 | 3 | student | receive the email when the claim has a result. | Tuan | Done
13 | 3 | 3 | student | view my claims and its result. | Tuan | Done
14 | 2 | 3 | administrator | change closure dates for each academic year | Sang | Done
15 | 4 | 4 | administrator | change items of assessment and their due dates | Sang | Done
16 | 2 | 3 | administrator | change students and passwords | Sang | Done
17 | 2 | 3 | administrator | manage user and roles | Sang | Done
18 | 1 | 2 | user | login to the system. | Tuan | Done
19 | 2 | 3 | user | specific role in the system | Sang | Done
20 | 3 | 3 | user | view this website in many devices such as mobile, web, | Sang | Done

## Sprint 1
Menber |  |  | Total | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
Sang |  |  | 4 |  | 2 | [6 empty] | 2
Tuan |  |  | 6 |  |  |  | 2 |  |  | 2 |  | 2
Duc |  |  | 0
Chau |  |  | 0
Backlog Item | Responsible | Estimate | Spend | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
As a manager, i want to view all the claim | Sang | 2 | 3 | [8 empty] | 3
As a user, i want to login to the system. | Tuan | 2 | 2 | [8 empty] | 2
main layout | Tuan | 1 | 1 |  |  |  | 1
Setup project + Git | Tuan | 1 | 1 |  |  |  | 1
ERD | Tuan | 2 | 2 | [6 empty] | 2
Setup scrum board + blacklog | Sang | 2 | 2 |  | 2
|  |  |  | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
Estimate |  |  | 10 | 10 | 8 | 8 | 6 | 6 | 6 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0
Burnout |  |  | 11 | 11 | 9 | 9 | 7 | 7 | 7 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint 2
Menber |  |  | Total | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
Sang |  |  | 14 | [7 empty] | 2 | 1 | 2 | 2 | 2 | 3 | 2
Tuan |  |  | 13 | [7 empty] | 3 | 2 | 1 | 1 | 1 | 3 | 2
Backlog Item | Responsible | Estimate | Spend | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
Fix database and the code related | Tuan | 2 | 2 | [7 empty] | 2
Fix US: As a manager, i want to view all the claim | Sang | 3 | 3 | [7 empty] | 3
As a user, I want to specific role in the system | Sang | 3 | 3 | [9 empty] | 3
As a Admin, I want to manage user and roles | Sang | 3 | 3 | [10 empty] | 3
As a admin, I want to change students and passwords | Sang | 3 | 3 | [11 empty] | 2 | 1
As a admin, I want to change closure dates for each academic year | Sang | 3 | 3 | [13 empty] | 3
As a student, I want to upload one or more the EC claim | Tuan | 3 | 4 | [9 empty] | 2 | 1 | 1
As a Coordinator, I want to receive a notification when there is a new claim | Tuan | 4 | 4 | [11 empty] | 1 | 2 | 1
As a Coordinator,I want to process the claim before 14 days since the upload date. | Tuan | 1 | 1 | [8 empty] | 1
As a Coordinator, I want to belong the faculty | Sang | 1 | 1 | [8 empty] | 1
As a Coordinator, I want to manage process for the faculty | Sang | 1 | 1 | [8 empty] | 1
|  |  |  | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
Estimate |  |  | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 22 | 19 | 16 | 13 | 10 | 4 | 0
Burnout |  |  | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 23 | 20 | 15 | 11 | 7 | 4 | 0

## Sprint 3
Menber |  |  | Total | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
Sang |  |  | 15 | 0 | 2 | 0 | 2 | 0 | 2 | 2 | 2 | 0 | 2 | 0 | 2 | 0 | 1
Tuan |  |  | 14 | 0 | 2 | 0 | 2 | 0 | 2 | 2 | 2 | 0 | 2 | 0 | 2 | 0 | 0
Backlog Item | Responsible | Estimate | Spend | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
As a manager, I want to view report | Sang | 6 | 7 | [9 empty] | 2 | 2 | 2 |  | 1
As a Coordinator, I want to access student claim in my faculty | Sang | 4 | 4 |  | 2 |  | 2
As a user, I want to view this website in many devices such as mobile, web | Sang | 6 | 8 | [5 empty] | 2 |  | 2 |  | 2 |  |  |  | 2
As a student, i want all of EC uploaded claim have to contain PDF or Image evidence. | Tuan | 4 | 4 |  | 2 |  | 1
As a student, i want to view my claims and its result. | Tuan | 2 | 2 | [5 empty] | 2
As a student, i want to receive the email when the claim has a result. | Tuan | 4 | 4 | [7 empty] | 2 | 2
As a Coordinator, i want to allow student upload evidence after closure date until final closure date | Tuan | 2 | 2 | [11 empty] | 2
As a Coordinator, I want to disable all claims uploading after closure date | Tuan | 2 | 2 |  |  |  | 2
|  |  |  | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
Estimate |  |  | 30 | 30 | 26 | 26 | 22 | 22 | 18 | 14 | 10 | 10 | 6 | 6 | 2 | 2 | 1
Burnout |  |  | 33 | 33 | 29 | 29 | 24 | 24 | 20 | 20 | 16 | 14 | 10 | 8 | 4 | 4 | 1

## Sprint 4
Menber |  |  | Total | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
Sang |  |  | 7 |  | 2 | 2 | 2 |  |  | 1
Tuan |  |  | 4 | 1 | 2 |  |  | 1
Backlog Item | Responsible | Estimate | Spend | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
Add search for Academy year Page | Sang | 1 | 1 |  | 1
Add search for Users page | Sang | 1 | 1 |  | 1
Add search for Assessments page | Sang | 1 | 1 |  |  | 1
Add search for Item page | Sang | 1 | 1 |  |  | 1
Us: As an administrator, I want to change items of assessment and their due dates | Sang | 2 | 3 |  |  |  | 3
Fix: As a Coordinator, I want process the claim before 14 days since the upload date. | Tuan | 1 | 1 |  |  |  |  | 1
Fix: As a User, I want to view this website in many devices such as mobile, web, | Sang | 1 | 1 | [6 empty] | 1
Add search for claim page | Tuan | 1 | 1 |  | 1
Fix: UI for claim page | Tuan | 1 | 1 |  | 1
Fix: Database | Tuan | 1 | 1 | 1
|  |  |  | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
Estimate |  |  | 11 | 10 | 6 | 4 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Burnout |  |  | 12 | 11 | 7 | 5 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0